## Sheet1
Bug ID | Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Environment
BUG-001 | Too many ads | Advertisements overwhelm the user interface, impacting usability. | 1. Open the app. 2. Navigate through different screens. 3. Observe the number and frequency of ads displayed. | Advertisements should not overwhelm the user experience and should be minimal. | Advertisements disrupt the user experience, making navigation difficult. | Medium | Low | Platform: Mobile App OS: iOS/Android
BUG-002 | Recent searches are not displayed | The app fails to display recent searches, even for logged-in users. | 1. Log in to the app. 2. Perform a few searches. 3. Check the recent searches section. | Recent searches should be displayed for logged-in users. | Recent searches are not displayed, even after performing multiple searches. | High | Medium | Platform: Mobile App OS: iOS/Android
BUG-003 | Cannot detect location | Location detection is not working | 1. Launch the app. 2. Allow location permissions. 3. Observe that the app fails to detect the location. | The app should detect the correct location when permissions are granted. | Location detection fails or defaults to an incorrect location. | High | High | Platform: Mobile App OS: iOS/Android
BUG-004 | Cannot add password | The app does not allow the user to set or save a password during sign-up. | 1. Begin the sign-up process. 2. Attempt to add a password. 3. Observe that the password cannot be saved. | The app should allow users to set and save a password during sign-up. | The app does not allow users to set or save a password. | High | High | Platform: Mobile App OS: iOS/Android
BUG-005 | No email verification | The app does not verify the user's email during the sign-up process, allowing invalid emails. | 1. Start the sign-up process. 2. Enter an invalid email address. 3. Complete the sign-up without any verification. | The app should verify the email address during sign-up to ensure validity. | Users can sign up with invalid or unverified email addresses. | Critical | High | Platform: Mobile App OS: iOS/Android